Valley College Logo

Citizens Building Oversight Committee

January 10, 2017

**Minutes**

**President’s Conference Room**

Members:

| **Name** | **Association** |
| --- | --- |
| Pat Ballew**\*** | Member of the College Foundation |
| Kevin Ary | Member at Large |
| Eric Bubbers | LACCD Representative |
| Asta Criss | Valley Glen Neighborhood Association |
| Lisa Cahan Davis | Studio City Neighborhood Council |
| Carlos Ferreyra | Greater Valley Glen Neighborhood Council |
| Diedra Stark | Retirees Association of LAVC |
| Vacant | Student Representative |
| Vacant | Valley Village Neighborhood Council |
| Vacant | Sherman Oaks Neighborhood Council |
| **Ex-Officio:** |  |
| Erika Endrijonas | College President |
| **Resource:** |  |
| Mark Strauss | College Project Director |
| Mike Lee | Vice President of Administrative Services |
| Armine Galukyan | Executive Assistant |

# Welcome and Introductions

Pat Ballew called the meeting to order at 6:00PM.

# Public comments

No public comments.

# Approval of Minutes

A motion was made and passed for the approval of the September 13, 2016 minutes.

# President’s Report- Erika Endrijonas

* Erika Endrijonas welcomed everyone to the new Administration and Career Advancement (“ACA”) building. The president’s office officially moved in on December 9, 2016.
* Los Angeles Valley College recently endured a cyber-attack, which is currently still under investigation. The cyber-attack impacted 71 of our servers; they encrypted the data, but didn’t take any of the data. We were randomly attacked and the district is looking at a new way to back up files to avoid this issue occurring in the future.

# Update on District Citizen’s Oversight Committee- Eric Bubbers

* Eric Bubbers reported on the meeting that was held on November 4, 2016. This was an irregular meeting scheduled solely for the purpose of reviewing and approving the annual report. The report was very comprehensive and thorough and can be found on the [BuildLACCD](http://www.buildlaccd.org/) website.
* There was a meeting scheduled on December 9th, which Bubbers wasn’t able to attend, but reviewed the minutes and everything was typical.
  + The audit reports are available on their website; they are focused on visible reports and transparency.
  + Measure CC- LACCD is confident and happy about the results. This measure will affect the District Citizen’s Oversight Committee (“DCOC”).
  + The DCOC is facing a challenge of trying to get a quorum at these meetings.
* In regards to Measure CC, Endrijonas mentioned the LACCD presidents have requested an update and are trying to get a timeline. For this campus, we are hoping more of the money in the reserves will become available to us so we can complete some other projects before moving on to Measure CC. Part of that money will be going towards security.

# Building Construction Update- Mark Strauss

* The ACA is now open for operation and Mark Strauss was very glad to hear everyone had a positive opinion on the project.
* Strauss reported on other projects that are currently underway:
  + VACC Project- there is a large basement and the deepest area is about 30 feet. This has created a large tunnel for rain to gather and a lot of water has been collecting even though many sandbags have been set up. The area is a very unsafe and the crew is waiting for the rain to stop before continuing with construction. In December, 27 days were lost due to weather conditions; the change order will be sent to Board of Trustees to extend the completion date. The original expected completion date was December 11th of 2018.
  + Central Plant & Thermal Plant- both projects have been in DSA for 8 to 9 weeks. So far, one round of comments came back and we have resubmitted.
  + ADA Project (4 bundles) - this project upgrades the accessibility in buildings not touched by other projects. DSA is currently overloaded and they are sending their work out to outside companies to take care of some of the projects. On average there is a 4 month delay/impact.
  + Gym Project- It is now in DSA and projected to cost 2 million dollars in total.
  + Storm Water Project (Underground Pipeline) - that project went out to bid and has been awarded. There will be a 50% cost spilt on the asphalt with LAUSD on certain locations. The storm water goes out to the wash in the LA River right on Coldwater Canyon. The storm water currently sits on the streets and creates a flood. DWP has plans in the future to use purple pipes all through the valley, but this can take many years.

We are able to capture water into a retention base by the student union, but currently, no program exists to store and reuse that water.

# Items from the Floor

* Endrijonas announced that there will be a ribbon cutting for the ACA building by the end of February 2017.

# Adjournment

Meeting adjourned at 6:36PM.